# McWay Site Management — Module 05: Senior Engineer Work Progress

# Detailed Specification for Odoo Implementation

Version: 1.0 (initial draft)

Date: 2026-04-21

Module Owner: Senior Engineer

Platform: Web (Odoo)

Prerequisite: Module 01 (Site Master, Lookup Lists — Layers), Module 03 (On-Site Dumping entries feed the Verification Queue), Module 02 & 04 (entries from camp/plant may also route to SE for verification when they affect a site the SE owns).

________________________________________

# Table of Contents

[Purpose & Scope](#1-purpose--scope)

[Odoo Implementation Strategy](#2-odoo-implementation-strategy)

[Menu & Navigation Structure](#3-menu--navigation-structure)

[Home / Dashboard](#4-home--dashboard)

[Sub-Module — Progress Entry (Method A)](#5-sub-module--progress-entry-method-a)

[Sub-Module — Chainage Strip View](#6-sub-module--chainage-strip-view)

[Sub-Module — Layer-Wise Summary](#7-sub-module--layer-wise-summary)

[Sub-Module — Progress History](#8-sub-module--progress-history)

[Sub-Module — Consolidated Verification Queue](#9-sub-module--consolidated-verification-queue)

[Method A vs Method B (Design Note)](#10-method-a-vs-method-b-design-note)

[Segment Model & Layer Hierarchy](#11-segment-model--layer-hierarchy)

[State Machine](#12-state-machine)

[Access Control](#13-access-control)

[Pre-loaded Demo Data & Walkthrough](#14-pre-loaded-demo-data--walkthrough)

[Design Decisions & Assumptions](#15-design-decisions--assumptions)

[Open Items / Notes for Developers](#16-open-items--notes-for-developers)

________________________________________

# 1. Purpose & Scope

The Work Progress Module is the Senior Engineer's (SE) command centre. It answers two questions every day: "how much road is done?" and "are the supervisors' entries accurate?"

The SE is responsible for:

Recording work progress against the site's planned chainage, layer by layer (GSB → WMM → BM → DBM → BC → SDBC → CC).

Visualising progress as a colour-coded chainage strip — a single screen that shows at a glance what's done, what's in progress, and what hasn't started.

Verifying downstream entries — dumping entries from Supervisors (Module 03), and — when relevant — camp/plant entries that flow into the SE's assigned site.

## In Scope

Progress Entry — layer-wise progress per chainage segment (Method A: status = Not Started / In Progress % / Complete).

Chainage Strip View — interactive colour-coded grid: X = chainage, Y = layers, cell colour = status.

Layer-Wise Summary — cumulative completion per layer (e.g., GSB 80%, WMM 60%).

Cumulative Site Progress — overall site completion %.

Progress History — audit-style list of all progress entries.

Consolidated Verification Queue — all submitted entries across modules that require SE sign-off, for the sites this SE owns.

## Out of Scope

Planned quantity / estimation — lives in Admin Portal → Estimation sub-module (Method B prerequisite). Progress here is entered as % or status, not quantity-based, in the demo.

Rework / snag list — not in demo scope.

BOQ / billing — separate concern; Reports module surfaces progress, but billing is phase 2.

Machine productivity — deferred to phase 2 (depends on per-machine capture, which is itself Phase 2).

________________________________________

# 2. Odoo Implementation Strategy

| Entity | Odoo Base | Strategy |
| --- | --- | --- |
| Progress Entry | Custom mcway.progress.entry | One record per chainage-segment × layer × date; state-managed |
| Chainage Segments | Derived from Site Master multi-segment chainage + configurable bucket size | Materialized on site creation / segment edit; one mcway.chainage.bucket per bucket |
| Layer Lookup | Lookup list (Module 01) | GSB / WMM / BM / DBM / BC / SDBC / CC — order matters (construction sequence) |
| Strip View | Custom QWeb + JS grid | Client-side render; server supplies bucket × layer matrix as JSON |
| Verification Queue | Union query across mcway.dumping.entry, mcway.camp.*, mcway.plant.* | Filtered to entries whose site (direct or via camp/plant linkage) is assigned to this SE |

## Dependencies (additional to Modules 01–04)

web, mail, auditlog — already in place.

## Performance Requirement

Per PRD: strip rendering for 27 km site with 7 layers (~1,890 cells) must complete ≤ 1.5 s. Approach: a single SQL query returning {bucket_id, layer_id, status, percent} with client-side painting on canvas or CSS grid.

________________________________________

# 3. Menu & Navigation Structure

The SE sees a scoped menu. They may be assigned to one or more sites (unlike the Supervisor who is one-to-one). Work progress is scoped to their assigned sites only.

📐 Work Progress
├── Home (Dashboard)
├── Site Selector (visible if SE owns >1 site)
├── Progress Entry
│   ├── New Entry
│   └── Bulk Entry (grid)          ← fast path; see §5.5
├── Chainage Strip View            ← hero visual
├── Layer-Wise Summary
├── Progress History
├── Verification Queue
│   ├── Dumping Entries
│   ├── Camp Entries (if SE's site is served by any camp)
│   └── Plant Entries (if SE's site is supplied by any plant)
└── Reports (site-level progress)
    ├── Daily Progress Report
    └── Cumulative Layer Report

│ Note: SE does NOT see Admin menus, cannot create sites, and cannot edit Supervisor or Camp In-charge data — only verify or request correction.

________________________________________

# 4. Home / Dashboard

Purpose: Single-screen snapshot of the SE's sites.

## 4.1 Site Context Strip (Persistent)

If the SE has multiple sites, a dropdown/pill bar at the top lets them switch. For single-site SEs, this is a read-only label.

## 4.2 Summary Tiles

| Tile | Value | Source |
| --- | --- | --- |
| Cumulative Site Progress | % overall | Weighted avg of all layers (see §7.3) |
| Today's Progress Entries | Count | Progress entries (today) |
| Layers at Risk | Count where behind schedule (if target exists) | §7.4 |
| Pending Verification | Count across all sub-queues | §9 |
| Dumping Entries This Week | Count (all states) | Module 03 feed |
| Active Chainage | e.g., "km 1.2–2.0" (where most recent progress activity happened) | Last N entries |
| Unverified Dumpings | Count (stale > 2d highlighted) | Module 03, state=submitted |

## 4.3 Mini Strip (Top of Home)

A compressed version of the Chainage Strip View — one-line-per-layer, hover for detail, click to open full Strip View.

## 4.4 Quick Actions

+ New Progress Entry — opens Progress Entry form.

Open Strip View — full strip visualisation.

Review Pending — opens Consolidated Verification Queue.

## 4.5 Recent Activity Feed

Last 10 progress entries + last 5 verification actions (verify / correction request). Each row: timestamp, type icon, description, state badge.

________________________________________

# 5. Sub-Module — Progress Entry (Method A)

Purpose: Record layer-wise progress at a specific chainage segment.

Odoo Model: mcway.progress.entry.

## 5.1 Form Fields

| # | Field | Type | Mandatory | Notes |
| --- | --- | --- | --- | --- |
| 1 | Entry Code | Char | Auto | PRG/YYYY/#### |
| 2 | Site | Many2one → Site | Auto / Select | Pre-filled if SE owns one site; dropdown if many |
| 3 | Date | Date | ✓ | Defaults to today; backdating allowed up to 3 days |
| 4 | Chainage Start | Integer (metres) | ✓ | Must align to segment boundary (snaps to nearest bucket) |
| 5 | Chainage End | Integer (metres) | ✓ | > Start; can span multiple buckets (see §5.3) |
| 6 | Side | Select | ✓ | LHS / RHS / Both / Lane / Median |
| 7 | Layer | Many2one → Layer lookup | ✓ | GSB / WMM / BM / DBM / BC / SDBC / CC |
| 8 | Status | Selection | ✓ | Not Started / In Progress / Complete |
| 9 | Percent Complete | Integer (0–100) | Conditional | Required if Status = In Progress. Auto = 0 if Not Started, 100 if Complete. |
| 10 | Photo(s) | Binary (multi) | ✗ | Up to 4 photos. Max 5 MB each, auto-compressed to 1080p. |
| 11 | Remarks | Text | ✗ | — |
| 12 | State | Selection | Auto | Draft → Submitted → Verified → Locked (see §12) |

## 5.2 Status → Percent Mapping

| Status | Percent | UX |
| --- | --- | --- |
| Not Started | 0 | Percent field hidden |
| In Progress | 1–99 | Percent field shown, mandatory; slider + number input |
| Complete | 100 | Percent field hidden (auto 100%) |

## 5.3 Chainage Span & Bucketing

Progress is stored at the bucket level (default 100 m). If the SE enters an entry spanning multiple buckets:

Example: Chainage 1200–1600 m, Layer = GSB, Status = Complete.

The system creates or updates 4 bucket records (1200–1300, 1300–1400, 1400–1500, 1500–1600), each stamped Complete @ 100%.

Each bucket record is atomic — if a subsequent entry updates just one bucket, the others are untouched.

Storage model: mcway.progress.bucket — one row per (site, bucket_start, side, layer). The mcway.progress.entry form creates/updates these buckets on save and stores the entry as an audit record pointing at the affected buckets.

## 5.4 Side Handling

If Side = Both, the bucket record is flagged as covering both LHS and RHS (logical union).

If Side = Lane or Median, separate rows are stored for those carriageway parts (matches Module 01 multi-side Site Master).

The strip view can be filtered to a specific side or show combined.

## 5.5 Bulk Entry Grid (Speed Path)

For the common case of "I completed layer X from chainage A to B this morning", a grid-entry form is offered:

Date: [2026-04-21]   Site: [Kalol Sanand]   Side: [LHS ▼]   Layer: [GSB ▼]

   Chainage (each cell = 100 m bucket)
   ┌────┬────┬────┬────┬────┬────┬────┬────┬────┬────┐
   │ 0.0│ 0.1│ 0.2│ 0.3│ 0.4│ 0.5│ 0.6│ 0.7│ 0.8│ 0.9│  ← km markers
   │ ✅ │ ✅ │ ✅ │ 🟡 │ ⬜ │ ⬜ │ ⬜ │ ⬜ │ ⬜ │ ⬜ │
   │100 │100 │100 │ 60 │  0 │  0 │  0 │  0 │  0 │  0 │  ← % (editable)
   └────┴────┴────┴────┴────┴────┴────┴────┴────┴────┘

   [Select range: drag across cells] [Set %: 100] [Apply]

Click or drag cells to select.

Set status/percent on selected cells in one action.

One save = many progress.bucket rows updated.

Works offline is not required — this is a web screen, not mobile.

## 5.6 Business Rules

Chainage within site segments. Entry chainage must fall within the site's defined segments (reuses Module 01 validation).

Layer order warning (non-blocking). If the SE records "BC complete" for a bucket where "BM" is still 40%, show a non-blocking warning: "BM at this chainage is 40%. Typical sequence is GSB → WMM → BM → DBM → BC → SDBC → CC. Continue?"

Percent range. 0–100 integer. In Progress status forces 1–99 (not 0 or 100).

Monotonic percent (recommended, non-blocking). If a bucket's layer was 60% yesterday and today's entry sets it to 40%, warn: "Progress is moving backwards for this bucket/layer. Possible correction — proceed?"

Photo recommended (not mandatory) for Complete status — the verifier relies on evidence.

Backdating limit: 3 days past; no future dates.

On submit: State → Submitted. Bucket(s) updated immediately. Appears in Verification Queue (self-verified for progress? see §13.1).

Edit after submit: SE can edit until verified (self-sign-off or admin sign-off — see §12).

________________________________________

# 6. Sub-Module — Chainage Strip View

Purpose: The hero visual. A colour-coded grid where each cell represents one 100 m bucket × one layer. Shows the entire site's progress at a glance.

Odoo Model: Server query, client-side render.

## 6.1 Layout

km 0.0  0.5   1.0   1.5   2.0   2.5   3.0   3.5   4.0 …
       ┌───────────────────────────────────────────────────────┐
  GSB  │███████████████████░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░│
       │100 100 100 100 60  0   0   0   0   0   0   0   …      │
  WMM  │█████████████░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░│
  BM   │███████░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░│
  DBM  │███░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░│
  BC   │░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░│
  SDBC │░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░│
  CC   │███░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░│
       └───────────────────────────────────────────────────────┘

## 6.2 Cell States & Colours

| Status | Colour | Example |
| --- | --- | --- |
| Not Started | Light grey (#e0e2e7) | 0% |
| In Progress 1–33% | Red-orange (#f4a261) | 20% |
| In Progress 34–66% | Yellow (#f4c430) | 50% |
| In Progress 67–99% | Light green (#8bc34a) | 80% |
| Complete 100% | Dark green (#198754) | 100% |
| Not Applicable | Hatched pattern | e.g., layer CC not planned for this segment |

## 6.3 Interactions

| Action | Behavior |
| --- | --- |
| Hover cell | Tooltip: "GSB @ km 0.3–0.4 (LHS) — In Progress 60% — last updated 2026-04-19 by Kiran Shah" |
| Click cell | Opens a side drawer with the full bucket history (all entries affecting this bucket × layer) |
| Drag across cells | Selects a range; "Quick Update Status" button appears |
| Layer row click | Filters Layer-Wise Summary to that layer |
| km marker click | Opens Progress History filtered to that chainage ± 100 m |

## 6.4 Filters

Side: All / LHS / RHS / Lane / Median (tabs)

Date Cursor: "as of today" (default) / "as of 2026-04-15" — see §6.5

Layers visible: multi-select chips to show/hide specific layers

Zoom: 100 m / 500 m / 1 km bucket aggregation for long sites

## 6.5 Time Travel

A date cursor shows the site's state as of that date. Server query filters progress buckets to date ≤ cursor. Useful for retrospective analysis and client reporting.

## 6.6 Export

PNG — strip rendered to image (for WhatsApp / email to owner)

PDF — landscape, with header (site name, date, overall %) and the strip + layer summary table

________________________________________

# 7. Sub-Module — Layer-Wise Summary

Purpose: Numeric roll-up per layer across the whole site.

## 7.1 Summary Table

| Layer | Buckets Total | Not Started | In Progress (avg %) | Complete | Overall % |
| --- | --- | --- | --- | --- | --- |
| GSB | 270 | 240 | 8 @ 55% | 22 | 9.8% |
| WMM | 270 | 260 | 3 @ 40% | 7 | 3.0% |
| BM | 270 | 267 | 2 @ 30% | 1 | 0.6% |
| DBM | 270 | 270 | 0 | 0 | 0.0% |
| BC | 270 | 270 | 0 | 0 | 0.0% |
| SDBC | 270 | 270 | 0 | 0 | 0.0% |
| CC | 270 | 267 | 0 | 3 | 1.1% |

## 7.2 Cell Calculation

Overall % = (Σ percent across all buckets for this layer) / (bucket count × 100) × 100

Layers can be excluded per segment (e.g., "CC not planned for segment 2") — those buckets are counted as "N/A" and removed from the denominator.

## 7.3 Cumulative Site Progress

Weighted average across all planned layers:

Cumulative % = Σ (layer weight × layer %) / Σ (layer weights)

Layer weights are configurable in Admin → System Thresholds (default: all equal). Typical weighting may give more weight to BC / DBM (costlier layers).

│ Pending from client: whether to enable weighted cumulative or simple average. Demo uses equal weights.

## 7.4 Behind-Schedule Flagging

If Admin defines target dates per layer (stretch / P0 goal), the summary shows 🔴 behind by X days or 🟢 on track. Deferred for demo — not all sites will have target dates loaded.

________________________________________

# 8. Sub-Module — Progress History

Purpose: Chronological audit list of all progress entries.

## 8.1 List View

| Column | Notes |
| --- | --- |
| Entry Code | PRG/2026/0042 |
| Date | — |
| Chainage | km 1.2–1.6 |
| Side | LHS / RHS / Both / Lane / Median |
| Layer | badge with colour |
| Status | badge (Not Started / In Progress X% / Complete) |
| Photos | 📷 × 2 (count) |
| Entered By | User name |
| State | Draft / Submitted / Verified / Locked |

## 8.2 Filters & Sorting

Date range

Layer

Side

State

Chainage range

Entered by (for sites with multiple SEs)

## 8.3 Drill-Down

Click an entry → read-only detail view with full field set, photos, affected buckets list, audit log (who edited when).

________________________________________

# 9. Sub-Module — Consolidated Verification Queue

Purpose: Single screen where the SE reviews entries across all downstream modules that affect their assigned site(s).

This is the SE's verification role (PRD F-E03).

## 9.1 What Reaches This Queue

| Source Module | Routes to SE When |
| --- | --- |
| Module 03 — On-Site Dumping | SE's site = the dumping entry's site |
| Module 02 — Camp Module | A camp that serves the SE's site (inward / outward / RMC / labor). Optional — Admin configurable |
| Module 04 — Plant Module | A plant that supplies the SE's site (inward / production / outward). Optional — Admin configurable |

│ Design decision: Dumping entries always route to SE (they happen on the site). Camp/Plant routing is opt-in per site via a System Threshold "SE verifies upstream entries for this site: yes/no". For the demo, enabled for Kalol Sanand.

## 9.2 Queue View

Tabs by source module. Each tab:

| Column | Notes |
| --- | --- |
| Entry Code | — |
| Type | Dumping / Camp Inward / Camp Outward / RMC / Labor / Plant Raw / Production / Plant Outward |
| Date | — |
| Description | Material, qty, chainage / camp / plant |
| Entered By | — |
| Age | "2h ago", "1d 4h" |
| Flags | ⚠️ variance / 📷 no photo / 🕒 stale |
| Actions | Verify / Request Correction |

## 9.3 Verification Actions

| Action | Effect |
| --- | --- |
| Verify | State → Verified. Verifier name + timestamp recorded. Removed from queue. |
| Request Correction | Remark sent to submitter. Entry stays in Submitted. Submitter sees badge on their entry and can edit + re-submit. |
| Bulk Verify | Select multiple → "Verify Selected". Useful for end-of-day review. |

## 9.4 Filters

Tab (source module)

Date range

Flagged only (⚠️)

Stale only (> 2 days, highlighted orange)

Material / Layer / Chainage (for dumping)

## 9.5 Rules (Recap)

Verification never blocks — entries are already live in stock, reports, dashboard.

Verifier cannot edit — only verify or request correction.

Audit trail: verifier, timestamp, IP (via mail.thread + auditlog).

Re-verification not required after Supervisor re-submits a corrected entry — but the entry does re-appear in the queue.

________________________________________

# 10. Method A vs Method B (Design Note)

Per Demo Documentation §9.1 and PRD Epic E, two methods are on the table.

| Aspect | Method A (Status / %) — recommended | Method B (Qty-based) |
| --- | --- | --- |
| Inputs | Status (Not Started / In Progress % / Complete) | Planned Qty (from Estimation) + Executed Qty |
| % calculation | Direct | Executed / Planned × 100 |
| Prerequisite | Layer lookup only | Estimation module with planned quantities |
| Objectivity | SE's judgement | Quantity-based, more objective |
| Demo readiness | ✅ Ready now | ❌ Needs Estimation module loaded with planned values |

Decision for demo: Method A. Method B is a phase-2 upgrade path — the progress.bucket schema includes optional planned_qty and executed_qty fields so Method B can layer on without migration.

│ Pending from client: confirm Method A is acceptable for demo. Ratify the phase-2 path to Method B.

________________________________________

# 11. Segment Model & Layer Hierarchy

## 11.1 Chainage Bucketing

| Site | Chainage Span | Bucket Size | # Buckets |
| --- | --- | --- | --- |
| Kalol Sanand (demo) | 0–27,000 m | 100 m | 270 |

Bucket size is configurable per site in Module 01 Site Master (default 100 m). Options: 50 m / 100 m / 250 m / 500 m. Smaller = more granular but heavier strip view.

## 11.2 Layer Hierarchy

Standard road construction sequence (bottom to top):

| Order | Layer | Full Name | Typical % of total cost |
| --- | --- | --- | --- |
| 1 | GSB | Granular Sub-Base | ~8% |
| 2 | WMM | Wet Mix Macadam | ~12% |
| 3 | BM | Bituminous Macadam | ~18% |
| 4 | DBM | Dense Bituminous Macadam | ~22% |
| 5 | BC | Bituminous Concrete | ~25% |
| 6 | SDBC | Semi-Dense Bituminous Concrete | ~10% |
| 7 | CC | Cement Concrete (culverts, drains, shoulders — often partial) | ~5% |

│ Note: SDBC is either applied OR BC is — rarely both. Configurable per segment in Admin → Site Master → Layer Plan (phase 2). For demo, all layers are available on all segments.

## 11.3 Layer × Bucket × Side Matrix

For Kalol Sanand (27 km, 7 layers, LHS+RHS):

270 buckets × 7 layers × 2 sides = 3,780 bucket rows

Strip view renders one side at a time by default (LHS shown first). Combined view merges LHS+RHS (AND = both must be done; OR = either suffices — configurable).

________________________________________

# 12. State Machine

Progress entries follow the same state model as other modules, with one wrinkle: SE can self-verify since they are themselves the verifier. For cross-check, Admin can configure a secondary verifier (typically Owner or another SE).

┌─────────┐     Save/Submit     ┌───────────┐      Verify      ┌──────────┐     Period Close     ┌────────┐
│  Draft   │ ─────────────────→ │ Submitted │ ───────────────→ │ Verified │ ──────────────────→ │ Locked │
└─────────┘                     └───────────┘                   └──────────┘                     └────────┘
                                      │                               │
                                      │ Edit (by SE)                  │ Unlock (Admin only)
                                      ↓                               ↓
                                 Back to Submitted               Back to Submitted

## 12.1 Self-Verification

| Site Setting | Who verifies SE progress entries |
| --- | --- |
| "SE self-verifies" (default) | SE. Entries auto-advance to Verified on submit. |
| "Secondary verifier required" | Admin or designated user. Entries stay Submitted until secondary verifies. |

For verification of downstream entries (dumping, camp, plant), SE is always the verifier. Self-verification does not apply — those entries originate from other users.

## 12.2 Notes

Stock/quantity impact is not relevant here — progress entries don't touch stock.

Report impact starts at Submitted — Submitted entries already contribute to cumulative % in dashboards. Verification is accountability, not a gate.

Edits after verified require Admin unlock, same pattern as other modules.

________________________________________

# 13. Access Control

## 13.1 Model-Level Access

| Model | SE (own sites) | Admin | Owner | Supervisor | Camp | Plant | Verifier |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Progress Entry | CRUD (own sites) | CRUD | R | R (own site) | — | — | R |
| Progress Bucket | CRUD (via entry) | CRUD | R | R | — | — | R |
| Strip View | R (own sites) | R | R | R (own site) | — | — | R |
| Verification Queue | Verify (own sites) | Verify | — | — | — | — | Verify |

## 13.2 Record Rules

SE sees only data for their assigned site(s) — enforced via ir.rule on user.assignment_target (polymorphic: may be multi-site).

SE can verify entries routed to their sites (dumping direct; camp/plant via linkage + System Threshold).

Admin sees all sites.

Owner is read-only.

## 13.3 Multi-Site SE

Unlike Supervisor / Camp In-charge / Plant In-charge (strictly one-to-one), an SE may own multiple sites. Assignment Type on the user record supports [Site(s)] (Many2many) specifically for the SE role.

│ Demo: Kiran Shah is assigned only to Kalol Sanand (single site). Multi-site is structurally supported but not demonstrated.

________________________________________

# 14. Pre-loaded Demo Data & Walkthrough

## 14.1 Demo Senior Engineer

Kiran Shah (USR/005) — role = Senior Engineer. Assigned site: Kalol Sanand. Preferences: metric km display, strip side = LHS by default.

## 14.2 Demo Site

Kalol Sanand — 27 km (0–27,000 m), single segment, LHS + RHS. Bucket size = 100 m → 270 buckets per side.

## 14.3 Pre-loaded Progress Entries (12 entries)

| # | Code | Date | Chainage | Side | Layer | Status | % | Photos | State |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | PRG/2026/0001 | 2026-04-10 | 0–1000 m | LHS | GSB | Complete | 100 | 2 | Verified |
| 2 | PRG/2026/0002 | 2026-04-11 | 1000–2000 m | LHS | GSB | Complete | 100 | 1 | Verified |
| 3 | PRG/2026/0003 | 2026-04-12 | 2000–2500 m | LHS | GSB | In Progress | 60 | 2 | Verified |
| 4 | PRG/2026/0004 | 2026-04-13 | 0–800 m | LHS | WMM | Complete | 100 | 1 | Verified |
| 5 | PRG/2026/0005 | 2026-04-14 | 800–1200 m | LHS | WMM | In Progress | 70 | 2 | Verified |
| 6 | PRG/2026/0006 | 2026-04-15 | 0–500 m | LHS | BM | Complete | 100 | 3 | Verified |
| 7 | PRG/2026/0007 | 2026-04-16 | 500–700 m | LHS | BM | In Progress | 40 | 1 | Verified |
| 8 | PRG/2026/0008 | 2026-04-17 | 0–300 m | LHS | DBM | In Progress | 50 | 1 | Submitted |
| 9 | PRG/2026/0009 | 2026-04-18 | 0–300 m | LHS | CC | Complete | 100 | 1 | Submitted |
| 10 | PRG/2026/0010 | 2026-04-19 | 1500–1700 m | RHS | GSB | Complete | 100 | 0 | Submitted |
| 11 | PRG/2026/0011 | 2026-04-20 | 0–200 m | LHS | BC | In Progress | 25 | 2 | Submitted |
| 12 | PRG/2026/0012 | 2026-04-21 | 200–400 m | LHS | DBM | In Progress | 30 | 1 | Draft |

## 14.4 Expected Layer-Wise Summary (LHS, after demo data)

| Layer | Buckets Complete | In Progress (avg) | Not Started | Overall % |
| --- | --- | --- | --- | --- |
| GSB | 20 | 5 @ 60% | 245 | 8.5% |
| WMM | 8 | 4 @ 70% | 258 | 4.0% |
| BM | 5 | 2 @ 40% | 263 | 2.1% |
| DBM | 0 | 5 @ 40% | 265 | 0.7% |
| BC | 0 | 2 @ 25% | 268 | 0.2% |
| SDBC | 0 | 0 | 270 | 0.0% |
| CC | 3 | 0 | 267 | 1.1% |

Cumulative LHS site progress (equal weights): ~2.4%.

## 14.5 Verification Queue (at demo time)

| Tab | Count | Highlights |
| --- | --- | --- |
| Dumping (Module 03) | 5 | 1 correction requested (pipe count); 1 stale (>24h) |
| Camp Entries | 4 | 1 stale (shuttering return >24h) |
| Plant Entries | 5 | 1 flagged ⚠️ variance (BC batch 10.7%); 1 stale |
| Total | 14 |  |

## 14.6 Demo Walkthrough (Suggested)

Log in as Kiran Shah (SE) → Home dashboard shows cumulative ~2.4%, mini strip, 14 pending verifications.

Open Chainage Strip View → full LHS grid for Kalol Sanand. Hover over GSB @ km 0.2–0.3 → tooltip shows 100% complete, entered by Kiran on 2026-04-10.

Drag across GSB cells km 2.5–3.0 → "Quick Update Status" appears → set 50% → save. Strip updates live.

Open Progress Entry → Bulk Entry Grid → show the grid input, drag & apply % for WMM km 1.2–1.5.

Switch side to RHS tab → show the RHS strip (mostly empty — only entry 10 covered 1500–1700 GSB).

Open Layer-Wise Summary → show per-layer %, drill into GSB → filtered progress history.

Open Verification Queue → Dumping tab → bulk-verify 3 entries, click "Request Correction" on the pipe-count entry → add remark → submit.

Switch to Camp Entries tab → verify the shuttering return entry.

Switch to Plant Entries tab → open the flagged BC batch, review variance, verify anyway with a remark.

Export Strip View as PNG → download → "share with Owner / WhatsApp".

________________________________________

# 15. Design Decisions & Assumptions

| # | Decision | Rationale |
| --- | --- | --- |
| 1 | Method A for demo (status + %) | Simpler to launch; Method B needs Estimation loaded first |
| 2 | 100 m default bucket size | Granular enough for accountability, coarse enough to render fast (≤1.5s) |
| 3 | Bucket × Layer × Side as the storage grain | Supports all visualisation and roll-up queries cleanly |
| 4 | Strip is the hero UI | Demo doc §9.3 and PRD F-E02 both emphasise visual progress; client owner will look here first |
| 5 | Layer-order warning is non-blocking | Real sites sometimes lay layers out of order (staging, weather); don't force sequence |
| 6 | Monotonic percent warning is non-blocking | Corrections should be allowed; warn but don't block |
| 7 | SE can self-verify progress entries | SE is the recording authority; blocking their own entries is circular. Secondary verifier is optional per site. |
| 8 | SE verifies downstream entries via consolidated queue | One screen, three tabs — reduces context switching for SE |
| 9 | Camp/Plant routing is opt-in per site | Some sites won't need SE sign-off on every camp/plant entry — Admin configures |
| 10 | Bulk entry grid | The #1 speed optimisation — 100 m × 7 layers = fiddly without bulk input |
| 11 | Strip export to PNG/PDF | Real outcome for the demo: client wants to share progress with owner via WhatsApp |
| 12 | Equal layer weights by default | Client hasn't provided weighted cost breakdown yet; defer |
| 13 | Time-travel date cursor | Retrospective analysis is a strong "wow" moment for management |
| 14 | N/A layer option via hatched cell | Some segments genuinely don't have certain layers (e.g., CC only on culverts) |
| 15 | Multi-site SE supported, not demonstrated | Structural support is free; demo keeps one SE = one site for clarity |
| 16 | Backdating limit 3 days | Consistent with Modules 02 / 03 / 04 |

________________________________________

# 16. Open Items / Notes for Developers

Method B activation — keep planned_qty and executed_qty nullable columns on progress.bucket. When Method B activates, migrate by populating planned_qty from the Estimation module; no schema change needed.

Layer weights — configurable in Admin → System Thresholds. Default = all equal. Plan a UI once client confirms weighted cumulative is desired.

Behind-schedule flagging — requires target dates per layer per segment. Defer until Admin → Schedule sub-module exists.

Strip performance — 270 buckets × 7 layers = 1,890 cells per side. Use CSS Grid with aria-labels; avoid DOM-per-cell for > 5,000 cells (zoom out to 500 m buckets or switch to canvas).

Strip export — use server-side headless Chromium (Odoo has wkhtmltopdf built-in, but canvas rendering may be cleaner via a dedicated endpoint).

Consolidated Verification Queue SQL — union of three source tables with computed site_id via site / camp→site / plant→site joins. Index on (state, site_id) recommended.

Multi-site SE UI — site selector pill bar at the top of all screens; persists in user preferences.

Layer plan per segment (Phase 2) — model: mcway.site.layer_plan with (site, segment, layer, applicable, planned_start_date, planned_end_date). Drives N/A cells and schedule flags.

Time-travel query — ensure the progress.bucket table has last_updated date and a history log; time-travel queries last_updated ≤ cursor_date to show as-of state.

Photo storage — photos on progress entries feed into reports. Keep references in ir.attachment linked via mail.thread.

LHS vs RHS vs Both — join semantics — document clearly: "Both" status is AND (LHS OR RHS must be 100% to count) unless the site configures OR semantics. Default to AND for safety.

Notification on correction request — in-app notification to the submitter (Supervisor / Camp / Plant In-charge); email optional for demo.

Bulk entry grid undo — support "undo last bulk apply" for 30 seconds after save. Prevents destructive mass edits.

Layer colour palette — use colour-blind-safe ramp for status (ColorBrewer's RdYlGn works, but swap saturated red for lighter shade to avoid panic).

Hover tooltip performance — debounce hover to 200 ms to avoid flicker on fast mouse movement.

Mobile view — SE is primarily desktop, but a read-only mobile view of the strip for quick field check-ins is a phase-2 nice-to-have.